## README
HealthLink EHR – Project Data Workbook (A2_GroupXX_ProjectData.xlsx)
Tabs:
Budget – task costs, BAC, contingency, and earned value inputs
Dashboard – PV, EV, AC, SV, CV, SPI, CPI and RAG status at the status date
Risks – risk register with scores; HeatMap – 5x5 heat map (counts per cell)
Stakeholders – register with power/interest; CommsPlan – communication plan
Quality – metrics and targets; ChangeLog – change requests; RACI – responsibility matrix
IssueLog – issues and corrective actions
Closure – closure checklist; Benefits – benefits realisation plan; Lessons – lessons learned so far

## Budget
Budget and Earned Value Inputs (status date 25 Sep 2026)
WBS | Task | Duration (days) | Resource 1 | Resource 2 | Combined rate ($/hr) | Labour cost ($) | Fixed cost ($) | Total planned cost ($) | Planned % complete at status date | Actual % complete at status date | Overrun days | PV ($) | EV ($) | AC ($) | Resource | Rate ($/hr)
1.1 | Project charter approved | 5 | Project Manager |  | 120 | 4800 | 0 | 4800 | 100% | 100% | 0 | 4800 | 4800 | 4800
1.2 | Stakeholder register & engagement plan | 5 | Business Analyst | Project Manager | 215 | 8600 | 0 | 8600 | 100% | 100% | 0 | 8600 | 8600 | 8600 | Project Manager | 120
1.3 | PM plan & baseline | 10 | Project Manager |  | 120 | 9600 | 0 | 9600 | 100% | 100% | 0 | 9600 | 9600 | 9600 | Business Analyst | 95
2.1 | Clinical workflow analysis (3 sites) | 15 | Business Analyst | Clinical Lead | 205 | 24600 | 0 | 24600 | 100% | 100% | 0 | 24600 | 24600 | 24600 | Clinical Lead | 110
2.2 | Requirements specification | 15 | Business Analyst | Clinical Lead | 205 | 24600 | 0 | 24600 | 100% | 100% | 0 | 24600 | 24600 | 24600 | EHR Vendor Consultant | 160
2.3 | Vendor tender & selection (incl. EHR licences) | 20 | Business Analyst | Project Manager | 215 | 34400 | 2400000 | 2434400 | 100% | 100% | 0 | 2434400 | 2434400 | 2434400 | Integration Developer | 130
3.1 | Network & hardware upgrade (incl. hardware) | 30 | Network/Infrastructure Engineer |  | 105 | 25200 | 650000 | 675200 | 100% | 100% | 0 | 675200 | 675200 | 675200 | Data Migration Specialist | 115
3.2 | EHR configuration & clinical templates | 40 | Clinical Lead | EHR Vendor Consultant | 270 | 86400 | 0 | 86400 | 100% | 100% | 10 | 86400 | 86400 | 108000 | Network/Infrastructure Engineer | 105
3.3 | Integrations (pathology, radiology, pharmacy) | 25 | Integration Developer |  | 130 | 26000 | 0 | 26000 | 40% | 0% | 0 | 10400 | 0 | 0 | Security & Privacy Officer | 115
3.4 | Privacy & security controls | 15 | Security & Privacy Officer |  | 115 | 13800 | 0 | 13800 | 66.67% | 0% | 0 | 9200.46 | 0 | 0 | Test Analyst | 85
4.1 | Legacy data cleansing & mapping | 25 | Business Analyst | Data Migration Specialist | 210 | 42000 | 0 | 42000 | 100% | 100% | 0 | 42000 | 42000 | 42000 | Trainer | 80
4.2 | Test data migrations (2 cycles) | 15 | Data Migration Specialist | Test Analyst | 200 | 24000 | 0 | 24000 | 66.67% | 0% | 0 | 16000.8 | 0 | 0
5.1 | System & integration testing | 15 | Integration Developer | Test Analyst | 215 | 25800 | 0 | 25800 | 0% | 0% | 0 | 0 | 0 | 0 | Hours per day | 8
5.2 | User acceptance testing | 10 | Clinical Lead | Test Analyst | 195 | 15600 | 0 | 15600 | 0% | 0% | 0 | 0 | 0 | 0
6.1 | Training materials & super-users | 20 | Clinical Lead | Trainer | 190 | 30400 | 0 | 30400 | 50% | 0% | 0 | 15200 | 0 | 0
6.2 | End-user training (all sites) | 20 | Trainer |  | 80 | 12800 | 0 | 12800 | 0% | 0% | 0 | 0 | 0 | 0
7.1 | Pilot go-live: Site A | 5 | Clinical Lead | Project Manager | 230 | 9200 | 0 | 9200 | 0% | 0% | 0 | 0 | 0 | 0
7.2 | Post-pilot review & fixes | 10 | Integration Developer | Project Manager | 250 | 20000 | 0 | 20000 | 0% | 0% | 0 | 0 | 0 | 0
7.3 | Rollout Sites B & C + final migration | 10 | Clinical Lead | Project Manager | 230 | 18400 | 0 | 18400 | 0% | 0% | 0 | 0 | 0 | 0
8.1 | Hypercare support | 20 | Clinical Lead | Test Analyst | 195 | 31200 | 0 | 31200 | 0% | 0% | 0 | 0 | 0 | 0
8.2 | Legacy decommissioning | 10 | Network/Infrastructure Engineer |  | 105 | 8400 | 0 | 8400 | 0% | 0% | 0 | 0 | 0 | 0
8.3 | Closure, lessons learned & benefits handover | 5 | Project Manager |  | 120 | 4800 | 0 | 4800 | 0% | 0% | 0 | 0 | 0 | 0
| TOTAL (BAC = Budget at Completion) |  |  |  |  | 500600 | 3050000 | 3550600 |  |  |  | 3361001.26 | 3310200 | 3331800
| Contingency reserve % | [6 empty] | 10%
| Contingency reserve ($) | [6 empty] | 355060
| Approved project budget ($) | [6 empty] | 3905660
Notes: Planned % = share of task duration that should be finished by 25 Sep 2026 per the baseline. 3.2 finished 10 working days late (Overrun days = 10), so 3.3, 3.4, 4.2 and 6.1 had not started.

## Dashboard
Project Status Dashboard – status date Fri 25 Sep 2026
Measure | Value | What it means
Budget at Completion (BAC) | 3550600 | Total planned cost of the project (from ProjectLibre costs)
Planned Value (PV) | 3361001.26 | Value of work that should be done by 25 Sep
Earned Value (EV) | 3310200 | Value of work actually done by 25 Sep
Actual Cost (AC) | 3331800 | What the completed work actually cost
Schedule Variance SV = EV − PV | -50801.26 | Negative = behind schedule
Cost Variance CV = EV − AC | -21600 | Negative = over budget
Schedule Performance Index SPI = EV / PV | 0.98489 | Below 1.00 = behind schedule
Cost Performance Index CPI = EV / AC | 0.99352 | Below 1.00 = over budget
Estimate at Completion EAC = BAC / CPI | 3573768.679 | Forecast final cost if current cost performance continues
Variance at Completion VAC = BAC − EAC | -23168.6786 | Forecast over/under run at completion
Critical path slip (working days, from ProjectLibre) | 10 | 3.2 finished 10 days late and is on the critical path
Days recovered by CR-02 (forecast) | 5 | Second vendor consultant on 3.3 (approved change CR-02)
Forecast go-live slip (working days) | 5 | Remaining delay to go-live forecast
Schedule RAG | AMBER | Rule: RED if SPI<0.95 or slip>10 days; AMBER if SPI<1 or any slip
Cost RAG | AMBER | Rule: RED if CPI<0.95; AMBER if CPI<1
Interpretation: SPI and CPI look close to 1.00 because the large fixed costs (licences, hardware) were already spent on time. The real problem is the critical path: 3.2 finished 10 days late, which pushes go-live back unless corrected. Look at the slip in days, not just the indices.

## Risks
Risk Register
ID | Risk (cause → event → effect) | Category | Likelihood (1–5) | Impact (1–5) | Score (L×I) | Rating | Owner | Response type | Response action | Linked WBS | Trigger / early warning | Status
R01 | Legacy data is incomplete or duplicated, so migrated records are wrong and patient safety is at risk | Data | 4 | 5 | 20 | High | Data Migration Specialist | Mitigate | Cleansing rules, 2 test migrations, clinician sample audit (≥99.5% accuracy) | 4.1, 4.2 | Test migration accuracy below 99.5% | Open
R02 | Clinicians resist the new workflow, so adoption is low after go-live | People | 4 | 4 | 16 | High | Clinical Lead | Mitigate | Clinician super-users, involve clinicians in UAT, targeted training | 6.1, 6.2 | Low training attendance; negative UAT feedback | Open
R03 | EHR configuration takes longer than planned, delaying go-live (critical path) | Schedule | 3 | 5 | 15 | High | Project Manager | Mitigate | Fixed-scope sprints, weekly progress review, vendor penalty clauses | 3.2 | Config sprint misses its target | Triggered – see ISSUE-01
R04 | Integration with pathology/radiology/pharmacy fails, so results don't reach clinicians | Technical | 3 | 5 | 15 | High | Integration Developer | Mitigate | Early interface testing, HL7/FHIR standards, vendor support | 3.3 | Interface test failures | Open
R05 | Privacy breach or unauthorised access to patient records | Compliance | 2 | 5 | 10 | Medium | Security & Privacy Officer | Avoid | Role-based access, audit logs, encryption, privacy impact assessment | 3.4 | Audit log anomalies | Open
R06 | Cutover downtime interrupts clinical care | Operational | 3 | 5 | 15 | High | Project Manager | Mitigate | Overnight cutover, paper downtime procedures, rollback plan | 7.1, 7.3 | Cutover rehearsal overruns | Open
R07 | Vendor tender takes longer due to procurement rules | Procurement | 3 | 3 | 9 | Medium | Business Analyst | Mitigate | Early market scan, pre-approved evaluation criteria | 2.3 | Tender clarifications extend deadline | Closed
R08 | Staff can't be released for training because of rostering | People | 4 | 3 | 12 | Medium | Trainer | Mitigate | Short modules, training across shifts, backfill budget | 6.2 | Booked sessions under 80% full | Open
R09 | Hardware or network delivery delayed at smaller sites | Supply | 2 | 3 | 6 | Low | Network/Infrastructure Engineer | Accept | Monitor; 35 days float on 3.1; order early | 3.1 | Supplier delivery notice slips | Closed
R10 | Cost overrun from change requests and scope creep | Cost | 3 | 4 | 12 | Medium | Project Sponsor | Mitigate | Change Control Board, 10% contingency reserve | All | CPI below 0.95 | Open
R11 | Key vendor consultant leaves mid-project | People | 2 | 4 | 8 | Medium | Project Manager | Transfer | Contract requires vendor replacement within 10 days | 3.2, 3.3 | Consultant resignation notice | Open
R12 | Legacy vendor support ends before decommissioning is complete | Technical | 2 | 4 | 8 | Medium | IT Operations Manager | Mitigate | Negotiate short support extension as fallback | 8.2 | Go-live slips past Feb 2027 | Open
Scoring: Likelihood 1 rare … 5 almost certain; Impact 1 negligible … 5 severe (patient safety, go-live, or >10% budget). Rating: High ≥15, Medium 8–14, Low ≤7.

## HeatMap
5×5 Risk Heat Map (number of risks in each cell)
Likelihood ↓ / Impact → | 1 | 2 | 3 | 4 | 5
5 | 0 | 0 | 0 | 0 | 0
4 | 0 | 0 | 1 | 1 | 1
3 | 0 | 0 | 1 | 1 | 3
2 | 0 | 0 | 1 | 2 | 1
1 | 0 | 0 | 0 | 0 | 0
Risk IDs by cell (for labelling the website image):
L4 × I5 = 20 | R01
L4 × I4 = 16 | R02
L3 × I5 = 15 | R03, R04, R06
L4 × I3 = 12 | R08
L3 × I4 = 12 | R10
L2 × I5 = 10 | R05
L3 × I3 = 9 | R07
L2 × I4 = 8 | R11, R12
L2 × I3 = 6 | R09
Legend: red = High (15–25), amber = Medium (8–14), green = Low (1–7)

## Stakeholders
Stakeholder Register
ID | Stakeholder | Role / interest in project | Power | Interest | Current engagement | Desired engagement | Strategy (power-interest quadrant) | Engagement actions
S01 | Network Chief Executive | Project sponsor | High | High | Supportive | Leading | Manage closely | Monthly steering committee; approves budget and go-live
S02 | Chief Medical Information Officer | Business owner / clinical sponsor | High | High | Supportive | Leading | Manage closely | Chairs clinical design authority; signs off UAT
S03 | Doctors (all sites) | End users | Medium | High | Resistant | Supportive | Keep informed → involve | Clinician champions, UAT involvement, demos
S04 | Nurses & Nurse Unit Managers | End users; release staff for training | Medium | High | Neutral | Supportive | Manage closely | Roster-friendly training, super-users on each ward
S05 | Health Information / Records team | Data owners | Medium | High | Neutral | Supportive | Keep informed | Data migration working group
S06 | IT Operations Manager | Runs infrastructure after handover | High | Medium | Supportive | Supportive | Keep satisfied | Technical working group; BAU handover plan
S07 | EHR Vendor | Supplier | High | Medium | Supportive | Supportive | Keep satisfied | Contract meetings, weekly delivery review
S08 | Privacy Commissioner / State Health Dept | Regulator | High | Low | Unaware | Neutral | Keep satisfied | Privacy impact assessment shared; compliance reports
S09 | Patients & community | Affected by record accuracy and downtime | Low | High | Unaware | Neutral | Keep informed | Hospital newsletter, signage during cutover
S10 | Finance Director | Budget control | High | Low | Neutral | Supportive | Keep satisfied | Monthly cost report (CPI, contingency)
S11 | Pathology, radiology & pharmacy departments | Integration partners | Medium | Medium | Neutral | Supportive | Keep informed | Interface testing sessions

## CommsPlan
Communication Plan
Communication | Audience | Content | Method | Frequency | Owner
Steering committee report | Sponsor, CMIO, Finance Director | Status, RAG, SPI/CPI, top risks, decisions needed | Meeting + written report | Monthly | Project Manager
Clinical design authority | CMIO, clinician champions | Configuration decisions, template sign-off | Workshop | Fortnightly | Clinical Lead
Project team stand-up | Project team, vendor | Progress, blockers, Trello board review | Video call | Daily (15 min) | Project Manager
Change Control Board | Sponsor, CMIO, IT Ops Manager | Change requests and impact | Meeting | Fortnightly / as needed | Project Manager
Staff newsletter & intranet | All staff | What's changing, training dates, go-live dates | Email / intranet | Fortnightly | Trainer
Ward huddles | Nurses, doctors | Training reminders, go-live readiness, quick tips | Face to face | Weekly before go-live | Super-users
Vendor delivery review | EHR Vendor | Deliverables, defects, contract milestones | Meeting | Weekly | Project Manager
Regulator compliance update | Privacy Commissioner / State Health Dept | Privacy impact assessment, security controls | Formal letter / report | At milestones M2 and M3 | Security & Privacy Officer
Patient notices | Patients & community | Downtime periods, what to expect | Signage, website | 2 weeks before each site go-live | Communications Officer

## Quality
Quality Requirements and Metrics
ID | Quality requirement | Metric | Target | How / when checked (quality control) | Linked WBS | Owner
Q1 | Data migration accuracy | % of sampled records matching source | ≥ 99.5% | Sample audit of 500 records per test cycle | 4.2, 7.3 | Data Migration Specialist
Q2 | Critical defects at go-live | Open severity-1 defects | 0 | Defect log review at readiness sign-off (M3) | 5.1, 5.2 | Test Analyst
Q3 | UAT pass rate | % of UAT scripts passed | ≥ 95% | UAT results report | 5.2 | Clinical Lead
Q4 | Staff trained before go-live | % of staff completing training | ≥ 95% | Training attendance records | 6.2 | Trainer
Q5 | System availability | Uptime during hypercare | ≥ 99.9% | Vendor monitoring report | 8.1 | IT Operations Manager
Q6 | Record retrieval time | Time to open full cross-site record | < 2 minutes | Timed sample, 3 months after go-live | Benefit B1 | Clinical Lead

## ChangeLog
Change Request Log
CR ID | Date raised | Raised by | Change requested | Impact (scope / time / cost) | Risk impact | Decision | Decided by / date
CR-01 | 14 Aug 2026 | CMIO | Add radiology image viewer to clinician workspace | Scope +; +5 days on 3.3 (non-critical at the time); +$12,000 | Low (uses existing interface) | Approved | CCB 21 Aug 2026
CR-02 | 18 Sep 2026 | Project Manager | Add second vendor consultant to 3.3 Integrations to recover 5 of 10 days lost on 3.2 | Schedule −5 days; cost +$25,600 (20 days × 8 h × $160) from contingency | Reduces R03/R04 exposure | Approved | CCB 22 Sep 2026
CR-03 | 21 Sep 2026 | Site B Director | Add patient-facing mobile app | Out of scope (exclusion); est. +$400,000 and +60 days | High | Rejected – refer to future project | CCB 22 Sep 2026

## RACI
RACI Matrix (R = Responsible, A = Accountable, C = Consulted, I = Informed)
Deliverable | Sponsor | CMIO | Project Manager | Business Analyst | Clinical Lead | EHR Vendor | IT Ops / Infrastructure | Security & Privacy Officer | Trainer
Project charter | A | C | R | C | C | I | I | I | I
Requirements specification | I | A | C | R | R | C | C | C | I
Vendor selection | A | C | R | R | C | I | C | C | I
EHR configuration | I | A | C | C | R | R | I | C | I
Integrations | I | C | A | C | C | R | R | C | I
Data migration | I | C | A | R | C | R | C | C | I
Privacy & security controls | I | C | A | I | I | C | C | R | I
Testing & UAT | I | A | C | C | R | R | C | C | I
Training | I | C | A | I | C | C | I | I | R
Go-live decision | A | R | R | I | C | C | C | C | I
Project closure | A | C | R | C | C | I | C | I | I
Rule check: each deliverable has exactly one A.

## IssueLog
Issue Log
ID | Date raised | Issue | Priority | Impact | Owner | Corrective action | Status
ISSUE-01 | 11 Sep 2026 | 3.2 EHR configuration not complete: clinicians requested template rework | High | Critical path slips 10 working days; go-live at risk | Project Manager | CR-02 approved: second vendor consultant on 3.3; start 6.1 in parallel with 3.3 | Resolved 25 Sep 2026 (3.2 complete, 10 days late); schedule recovery in progress
ISSUE-02 | 29 Sep 2026 | Pharmacy system vendor late supplying interface specification | Medium | Part of 3.3 blocked; could erode the 5 days recovered | Integration Developer | Escalated to vendor account manager; build pathology and radiology interfaces first | Open – due 6 Oct 2026
ISSUE-03 | 22 Sep 2026 | Site C training room unavailable in November | Low | 6.2 training at Site C may slip | Trainer | Book community clinic room; add online modules | Open

## Closure
Project Closure Checklist
Closure item | Owner | Status
Sponsor acceptance of all deliverables | Sponsor | Planned
All sites live and stable (M4) | Project Manager | Planned
Hypercare exit criteria met | IT Operations Manager | Planned
Open defects handed to BAU support | IT Operations Manager | Planned
Legacy systems decommissioned and data archived | IT Operations Manager | Planned
Vendor contract deliverables confirmed and final payment | Finance Director | Planned
Final cost report and contingency reconciled | Project Manager | Planned
Lessons learned workshop held and recorded | Project Manager | Planned
Benefits owners confirmed and measurement scheduled | Sponsor | Planned
Project documents archived | Project Manager | Planned
Team released and thanked | Project Manager | Planned

## Benefits
Benefits Realisation Plan
ID | Benefit | Measure | Baseline | Target | When measured | Benefit owner
B1 | Faster access to full patient records | Time to retrieve cross-site record | ~20 min | < 2 min | 3 months after go-live | CMIO
B2 | Fewer medication errors from missing information | Medication incidents per 1,000 admissions | Baseline FY2026 | −20% | 12 months after go-live | Director of Pharmacy
B3 | Less duplicate testing | Repeat pathology tests within 48 h | Baseline FY2026 | −15% | 12 months after go-live | Pathology Director
B4 | Lower legacy support costs | Annual support and licence cost of old systems | 4 systems | Decommissioned | After 8.2 | IT Operations Manager
B5 | Better compliance and audit | Records with complete audit trail | Partial | 100% | At go-live | Security & Privacy Officer

## Lessons
Lessons Learned (to date)
Area | What happened | Recommendation for future projects
Clinical involvement | Template rework on 3.2 happened because clinicians reviewed designs late | Hold clinician review at the end of every configuration sprint, not only at the end
Critical path focus | SPI/CPI looked healthy while the critical path slipped | Report critical-path slip in days alongside SPI/CPI on the dashboard
Change control | CR-03 (mobile app) was assessed and rejected quickly because exclusions were written in the scope statement | Keep exclusions explicit in every scope document
Vendor dependencies | Third-party pharmacy vendor was not in the communication plan early enough (ISSUE-02) | Add all integration partners to the stakeholder register at initiation
Tool integration | Using the same WBS codes in ProjectLibre, Trello and the risk register made tracing issues fast | Set a WBS coding standard on day 1